## 📊 Dashboard
HATE CRIME SUPPORT PROJECT ¦ WEST LONDON EQUALITY CENTRE ¦ City Bridge Foundation
Nov 2025 – Oct 2030 ¦ £480,801 ¦ 5-Year Monitoring Dashboard ¦ All figures update automatically from data sheets
⚡ FUNDER QUICK-ANSWER PANEL — Instant answers to common funder questions
Total Clients to Date |  |  | % from Ealing |  |  | Active Cases |  |  |  |  | % Under 25 |  |  |  |  | % of 5-Year Target Met
6 |  |  | 50% |  |  | 5 |  |  |  |  | 0% |  |  |  |  | 0.8%
% from Hillingdon |  |  | % from Hounslow |  |  | % Female |  |  |  |  | High Risk Cases |  |  |  |  | Referrals This Quarter
33.33% |  |  | 16.67% |  |  | 50% |  |  |  |  | 3 |  |  |  |  | 1
5-YEAR PROGRESS TRACKER — Cases handled vs target per year
Year 1 (2025-26) |  | Year 2 (2026-27) |  |  | Year 3 (2027-28) |  |  | Year 4 (2028-29) |  |  |  | Year 5 (2029-30) |  |  |  | Total (5 Years)
Target: 50 |  | Target: 100 |  |  | Target: 150 |  |  | Target: 200 |  |  |  | Target: 250 |  |  |  | Target: 750
4 |  | 2 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 6
8% |  | 2% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  |  | 0.8%
Note: Targets shown above are CUMULATIVE 5-year totals. Annual target: 50 cases per year.
OUTCOME PERFORMANCE TRACKER — 5 Key Outcomes ¦ Updates live from Outcome Tracker
Outcome |  |  |  |  | 5-Yr Target |  | Yr 1 |  |  | Yr 2 |  |  | Yr 3 |  |  | Yr 4 |  | Yr 5 |  | % Met
Improved access to legal advice & casework support |  |  |  |  | 80% reporting better access |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 6.25%
Empowered victims — confidence to report hate crime |  |  |  |  | 60% increase in reporting |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 5%
Strengthened collaboration among stakeholders |  |  |  |  | 20 formal partnerships |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 5%
Increased awareness of HC reporting & prevention |  |  |  |  | 85% report increased knowledge |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 7.059%
Sustainable community-led solutions |  |  |  |  | 10 grassroots-led initiatives |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0%
LIVE CLIENT BREAKDOWN — Auto-calculated from Client Intake
CLIENTS BY BOROUGH | [5 empty] | BY AGE GROUP | [8 empty] | BY GENDER
Ealing | Hillingdon |  |  | Hounslow |  | Under 25 |  |  | 25-49 |  |  | 50+ |  |  | Female |  | Male |  | Non-binary/Other
3 | 2 |  |  | 1 |  | 0 |  |  | 0 |  |  | 0 |  |  | 3 |  | 2 |  | 0
RISK LEVELS — Live from Client Intake
High Risk |  |  |  |  | Medium Risk | [7 empty] | Low Risk
3 |  |  |  |  | 2 | [7 empty] | 1
QUARTERLY SNAPSHOT — Set dates in ⚙ Settings tab
Clients This Quarter |  |  |  | Activities This Quarter |  |  |  | Cases Closed This Quarter | [5 empty] | New Referrals This Quarter
1 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 1
VOLUNTEERS & TRAINING — Live from Volunteer Log
Active Volunteers |  |  |  | Total Hours Volunteered |  |  |  | Fully Trained Volunteers | [5 empty] | Training Sessions Delivered
4 |  |  |  | 54 |  |  |  | 0 | [5 empty] | 4

## 📋 Client Intake
CLIENT INTAKE FORM ¦ Hate Crime Support Project ¦ WLEC
Record full client profile at START of journey. One row per client. Use 📊 Outcome Tracker to log progress at any point during the project.
ℹ️ All dropdown fields are required for dashboard reporting. Client Ref auto-generates as HC/1, HC/2 etc. Full Name column is for internal use only — treat as confidential. | [13 empty] | NATURE OF INCIDENT — tick all that apply
Client Ref (Auto) | Full Name | Initials / Anonymised ID | Caseworker / Support Worker | Date Referred | Case Status | Borough | Referral Source | Age Group | Gender Identity | Ethnic Origin | Religion | Risk Level | Type of Hate Crime | Harassment /ASB | Verbal Abuse | Physical Assault | Criminal Damage | Online Abuse | Stalking | Hate Incident | Other Incident | Reported to Police? | First Language | Sexual Orientation | Disability / Medical Condition | Housing Situation | Project Year | Presenting Issue (Brief Description)
HC/1 | Freda Ritchie 1 | FR1 | Omer Ul-haque | 2026-05-26 | Active | Ealing | Other | 26-55 | Female | White: British | Prefer not to say | High | Homophobic | ✓ | [7 empty] | Yes – no action taken | English | Do not wish to state | Mental Health | Other | Year 1 | Homophobia, within shared accomodation, issues with other tenant.
HC/2 | Freda Ritchie 2 | FR2 | Paula Howell | 2025-12-10 | Active | Hillingdon | Self-Referral | 18-25 | Male | Black: Caribbean | Christian | Medium | Racial | ✓ | ✓ | [6 empty] | No | English | Straight | None | Social housing | Year 1 | Racial abuse from neighbour, ongoing over 6 months.
HC/3 | Freda Ritchie 3 | FR3 | Reena Malhan | 2026-01-15 | Active | Ealing | MPS (Police) | 26-55 | Female | Asian: Pakistani | Muslim | High | Religious | ✓ |  |  |  | ✓ |  |  |  | Yes | Other | Prefer not to say | None | Owner occupier | Year 1 | Religiously motivated harassment at workplace.
HC/4 | Freda Ritchie 4 | FR4 | Omer Ul-haque | 2026-02-20 | Closed | Hounslow | Citizens Advice | 55-65 | Male | White: Irish | No religion | Low | Disability | ✓ | [7 empty] | Yes – no action taken | English | Straight | Mobility | Owner occupier | Year 1 | Disability hate crime — verbal abuse on public transport.
HC/5 | Freda Ritchie 5 | FR5 | Paula Howell | 2026-11-05 | Active | Ealing | Victim Support | Under 18 | Non-binary | Mixed: White/Asian | Buddhist | High | Homophobic | ✓ | ✓ |  |  |  | ✓ |  |  | No | English | Not Sure | Mental Health | Social housing | Year 2 | Homophobic bullying at school, online threats via social media.
HC/6 | Freda Ritchie 6 | FR6 | Reena Malhan | 2026-12-03 | Active | Hillingdon | Hillingdon Refugee Support Organisation | 26-55 | Female | Middle Eastern | Muslim | Medium | Racial | ✓ | ✓ | [6 empty] | Unknown | Other | Do not wish to state | None | Temporary/hostel | Year 2 | Racial and religious hate crime, client is asylum seeker.

## 📊 Outcome Tracker
OUTCOME TRACKER ¦ Hate Crime Support Project ¦ WLEC
Add a row each time you assess a client — at Intake, 3 months, 6 months, case closure, or any funder review. Multiple rows per client = full progress picture.
ℹ️ Use same Client Ref as Client Intake. Column Q auto-scores 'Yes' responses. Dashboard counts feed from this sheet. ¦ Greyed columns (K, L, M, O) are optional — complete when available. Core outcomes are columns E–I.
Client Ref | Assessment Date | Assessment Stage | Caseworker | O1: Better Access to Legal Support (Y/N) | O2: Increased Confidence to Report (Y/N) | O3: Strengthened Partnership Engaged (Y/N) | O4: Increased Awareness of HC (Y/N) | O5: Community-Led Solution Initiated (Y/N) | Project Year | Satisfaction Rating (1-5) (Optional) | Knowledge Score (pre) (Optional) | Knowledge Score (post) (Optional) | Reported to Police? (Y/N) | Referred to Partner Org? (Optional) | Outcome Score (Auto) | Notes / Evidence
HC/1 | 2026-05-26 | Intake | Omer Ul-haque | No | No | No | Yes | No | Year 1 |  |  |  | Yes | No | 1 | Client newly referred — initial legal advice provided. Confidence low.
HC/2 | 2025-12-10 | Intake | Paula Howell | No | No | No | No | No | Year 1 |  |  |  | No | No | 0 | Client referred self following racial abuse. Very distressed at intake.
HC/3 | 2026-01-15 | Intake | Reena Malhan | No | No | No | No | No | Year 1 |  |  |  | Yes | No | 0 | High risk case — religious hate crime at workplace. Referred to legal team.
HC/4 | 2026-02-20 | Intake | Omer Ul-haque | Yes | No | No | Yes | No | Year 1 |  |  |  | Yes | No | 2 | Client aware of legal rights. Case closed after resolution with transport authority.
HC/2 | 2026-03-10 | 3 Month Review | Paula Howell | Yes | No | No | Yes | No | Year 1 | 3 |  |  | No | Yes | 2 | Client engaged with community awareness session. Referred to Victim Support.
HC/1 | 2026-08-26 | 3 Month Review | Omer Ul-haque | Yes | Yes | No | Yes | No | Year 1 | 4 |  |  | Yes | No | 3 | Significant improvement in confidence. Legal case progressing.
HC/3 | 2026-07-15 | 6 Month Review | Reena Malhan | Yes | Yes | Yes | Yes | No | Year 1 | 4 | 2 | 4 | Yes | Yes | 4 | Strong progress — employer mediation successful. Referred to partnership org.
HC/4 | 2026-05-20 | Case Closure | Omer Ul-haque | Yes | Yes | No | Yes | No | Year 1 | 5 |  |  | Yes | No | 3 | Case closed positively. Client satisfied with outcome. Transport authority issued apology.
HC/5 | 2026-11-05 | Intake | Paula Howell | No | No | No | No | No | Year 2 |  |  |  | No | No | 0 | Young non-binary client — homophobic bullying and online threats. High priority.
HC/6 | 2026-12-03 | Intake | Reena Malhan | No | No | No | No | No | Year 2 |  |  |  | No | No | 0 | Asylum seeker — language barrier. Interpreter arranged. Complex case.
OUTCOME ACHIEVEMENT SUMMARY — Auto-calculated
Outcome |  |  |  | Yes | Partial | No | N/A | Achievement %
O1 – Better access to legal advice & casework |  |  |  | 5 | 0 | 5 | 0 | 50%
O2 – Increased confidence to report |  |  |  | 3 | 0 | 7 | 0 | 30%
O3 – Strengthened partnership engaged |  |  |  | 1 | 0 | 9 | 0 | 10%
O4 – Increased awareness of HC |  |  |  | 6 | 0 | 4 | 0 | 60%
O5 – Community-led solution initiated |  |  |  | 0 | 0 | 10 | 0 | 0%

## 🔀 Referral Tracker
REFERRAL TRACKER ¦ Hate Crime Support Project ¦ WLEC
Track all incoming referrals TO the project and outgoing referrals FROM the project to partner services.
REFERRAL SOURCE SUMMARY — Auto-calculated from log below
Referral Source |  |  |  | Count |  |  | % of Total |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Victim Support |  |  |  | 1 |  |  | 20% |  |  | 0 | 1 | 0 | 0 | 0
Age UK |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
MENCAP |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Spectra |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
ECIL |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
MPS (Police) |  |  |  | 1 |  |  | 20% |  |  | 1 | 0 | 0 | 0 | 0
Local MP / Councillor |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Self-Referral |  |  |  | 1 |  |  | 20% |  |  | 1 | 0 | 0 | 0 | 0
CATCH |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Community Security Trust |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Galop |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
MARAC |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Housing Association |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Council Safer Communities |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Citizens Advice |  |  |  | 1 |  |  | 20% |  |  | 1 | 0 | 0 | 0 | 0
Legal Aid Organisation |  |  |  | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 1 |  |  | 20% |  |  | 1 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 5
REFERRAL LOG — Add each referral below
Date | Client Ref | Initials | Direction | Referred By / To | Reason | Borough | Risk | Date Ack'd | Date Actioned | Outcome | Follow-up? | Follow-up Date | Caseworker | Year | Notes

## 📅 Activities
PROJECT ACTIVITIES & DELIVERABLES ¦ Hate Crime Support Project ¦ WLEC
5-YEAR ACTIVITY TARGETS (from M&E Framework)
Activity | Y1 Target | Y2 Target | Y3 Target | Y4 Target | Y5 Target | Actual to Date | % of Y5 Target
Hate crime cases handled | 50 | 50 | 50 | 50 | 50 | 4 | 8%
Awareness workshops delivered | 10 | 15 | 15 | 15 | 15 | 1 | 6.667%
New volunteers recruited | 0 | 15 | 0 | 0 | 0 | 0 | 0%
Formal agency partnerships | 5 | 10 | 15 | 18 | 20 | 0 | 0%
Community-led initiatives | 0 | 2 | 5 | 7 | 10 | 0 | 0%
Beneficiary surveys completed | 50 | 50 | 50 | 50 | 50 | 0 | 0%
Training sessions delivered | 10 | 15 | 15 | 15 | 15 | 1 | 6.667%
Stakeholder interviews (annual) | 0 | 1 | 1 | 1 | 1 | 0 | 0%
Community feedback forums | 2 | 4 | 4 | 4 | 4 | 0 | 0%
Policy recommendations published | 0 | 0 | 0 | 1 | 1 | 0 | 0%
ACTIVITY LOG — Add each event or session below
Date | Activity Title | Activity Type | Borough | Location / Venue | Lead Worker | Participants | New Referrals Generated | Project Year | Outcome / Notes
2026-02-14 | Hate Crime Awareness Workshop – Ealing | Workshop | Ealing | Ealing Civic Centre, New Broadway | Omer Ul-haque | 35 | 3 | Year 1 | O4: Increased Awareness of HC
2026-03-08 | Caseworker Training Session – WLEC | Training Session | Ealing | WLEC Office, Uxbridge Road | Reena Malhan | 12 | 0 | Year 1 | O1: Better Access to Legal Support

## 🙋 Volunteer Log
VOLUNTEER LOG ¦ Hate Crime Support Project ¦ WLEC
Track all volunteers, their training status, hours, DBS, and activity. Numbers feed Dashboard and Quarterly Report automatically.
⚡ VOLUNTEER SUMMARY — Auto-calculated
Total Volunteers Registered |  |  |  | Currently Active |  |  |  | Total Hours Volunteered |  |  |  | Fully Trained (All Modules)
4 |  |  |  | 4 |  |  |  | 54 |  |  |  | 0
VOLUNTEER REGISTER — One row per volunteer
Ref | Full Name | Role / Specialism | Date Joined | Borough(s) | Training Status | Status | DBS Date | DBS Expiry | Total Hours | Cases Supported | Activities Led | Languages | Accessibility Needs | Year Joined | Notes
VOL-001 | Freda Ritchie 1 | Community Outreach Volunteer | 2025-11-01 | Ealing | Fully Trained | Active | 2025-10-15 | 2027-10-15 | 24 | 3 | 2 | English | None | Year 1 | Freda Ritchie Test 1 — Volunteer since project launch
VOL-002 | Freda Ritchie 2 | Legal Support Volunteer | 2026-01-10 | Hillingdon | In Progress | Active | 2025-12-01 | 2027-12-01 | 16 | 2 | 1 | English, Urdu | None | Year 1 | Freda Ritchie Test 2 — Bilingual volunteer, training modules 1-4 complete
VOL-003 | Freda Ritchie 3 | Admin & Data Support Volunteer | 2026-03-05 | Ealing | Fully Trained | Active | 2026-02-20 | 2028-02-20 | 10 | 0 | 1 | English | None | Year 1 | Freda Ritchie Test 3 — Assists with client intake data entry
VOL-004 | Freda Ritchie 4 | Community Liaison Volunteer | 2026-11-15 | Hounslow | Not Started | Active | 2026-10-30 | 2028-10-30 | 4 | 1 | 0 | English, Somali | None | Year 2 | Freda Ritchie Test 4 — Year 2 recruit, training not yet commenced
VOLUNTEER HOURS LOG — Record each session
Date | Ref | Name | Activity / Task | Activity Type | Borough | Hours | Supervised By | Notes

## 🎓 Training Register
TRAINING REGISTER ¦ Hate Crime Support Project ¦ WLEC
Record every training session delivered — staff, volunteers, and partner/community training.
⚡ TRAINING SUMMARY
Total Sessions Delivered |  |  |  | Total Participants |  |  |  | Staff Trained |  |  |  | Volunteers Trained |  |  |  | Partners Trained
5 |  |  |  | 87 |  |  |  | 1 |  |  |  | 0 |  |  |  | 0
TRAINING SESSION LOG
Date | Training Title | Topic / Content | Audience | Year | Delivered By | Location | Participants | Hours | Borough | Method | Pre-Assessment | Post-Assessment | Certificate? | Feedback (1-5) | Evidence Ref | Follow-up? | Notes
2026-02-14 | Hate Crime Awareness & Reporting (Test: Freda Ritchie 1) | Definition of hate crime, reporting pathways, victim support | Staff & Volunteers | Year 1 | Freda Ritchie | Ealing Civic Centre, New Broadway | 35 | 3 | Ealing | In-person | 3 | 4 | Yes | 5 | HCSP-TR-001 | No | Freda Ritchie Test 1 — Workshop linked to awareness campaign
2026-03-08 | Caseworker Skills Training (Test: Freda Ritchie 2) | Case recording, outcome measurement, client confidentiality | Staff | Year 1 | Freda Ritchie | WLEC Office, Uxbridge Road | 12 | 2.5 | Ealing | In-person | 3 | 5 | Yes | 4 | HCSP-TR-002 | No | Freda Ritchie Test 2 — Internal staff training on M&E system
2026-05-20 | Online Safety & Cyber Hate (Test: Freda Ritchie 3) | Online hate crime, evidence gathering, reporting to platforms | Community & Volunteers | Year 1 | Freda Ritchie | Zoom (Online) | 22 | 2 | Other West London | Online | 2 | 4 | No | 4 | HCSP-TR-003 | Yes | Freda Ritchie Test 3 — Follow-up session planned for Q3
2026-11-10 | Partnership & Referral Pathways (Test: Freda Ritchie 4) | Working with statutory agencies, referral protocols, data sharing | Staff & Partners | Year 2 | Freda Ritchie | Hillingdon Civic Centre | 18 | 3 | Hillingdon | In-person | 3 | 5 | Yes | 5 | HCSP-TR-004 | No | Freda Ritchie Test 4 — Year 2 partner agency training
VOLUNTEER TRAINING COMPLETION MATRIX — ✅ = Complete ⬜ = Outstanding
Volunteer Name | HC Law & Legislation | Safeguarding | Unconscious Bias | Trauma- Informed | GDPR / Data Protection | Community Trigger | LGBTQI+ Awareness | Disability HC | % Complete
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%
| ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | ⬜ | 0%

## 📈 KPI Trends
KPI TREND CHARTS ¦ 5-Year Progress ¦ Hate Crime Support Project ¦ WLEC
Update yellow cells with actual data each year/quarter. Charts update automatically. Use for funder reports and annual reviews.
TABLE 1 — Cases Handled Per Year vs Target | [10 empty] | TABLE 2 — Outcome Achievement Per Year (% of beneficiaries)
Metric | Y1 Target | Y1 Actual | Y2 Target | Y2 Actual | Y3 Target | Y3 Actual | Y4 Target | Y4 Actual | Y5 Target | Y5 Actual | Outcome | Y1 | Y2 | Y3 | Y4 | Y5 | 5-Yr Target
Cases Handled | 50 | 4 | 100 | 2 | 150 | 0 | 200 | 0 | 250 | 0 | O1 – Better access to legal support | 0% | 0% | 0% | 0% | 0% | 80%
Workshops Delivered | 10 | 1 | 15 | 0 | 15 | 0 | 15 | 0 | 15 | 0 | O2 – Confident to report | 0% | 0% | 0% | 0% | 0% | 60%
New Partnerships | 5 | 0 | 10 | 0 | 15 | 0 | 18 | 0 | 20 | 0 | O3 – Partnership strengthened | 0% | 0% | 0% | 0% | 0% | 20%
[11 empty] | O4 – Increased awareness | 0% | 0% | 0% | 0% | 0% | 85%
[11 empty] | O5 – Community-led initiatives | 0% | 0% | 0% | 0% | 0% | 10
TABLE 3 — Clients by Borough Per Year | [10 empty] | TABLE 4 — Risk Levels & Reporting to Police
Year | Ealing | Hillingdon | Hounslow | Total | [6 empty] | Year | High Risk | Medium | Low | Reported to Police | Not Reported
Year 1 | 2 | 1 | 1 | 4 | [6 empty] | Year 1 | 2 | 1 | 1 | 1 | 1
Year 2 | 1 | 1 | 0 | 2 | [6 empty] | Year 2 | 1 | 1 | 0 | 0 | 1
Year 3 | 0 | 0 | 0 | 0 | [6 empty] | Year 3 | 0 | 0 | 0 | 0 | 0
Year 4 | 0 | 0 | 0 | 0 | [6 empty] | Year 4 | 0 | 0 | 0 | 0 | 0
Year 5 | 0 | 0 | 0 | 0 | [6 empty] | Year 5 | 0 | 0 | 0 | 0 | 0

## 📝 Quarterly Report
HATE CRIME SUPPORT PROJECT ¦ WEST LONDON EQUALITY CENTRE
QUARTERLY MONITORING REPORT ¦ Q1 2025-26 ¦ City Bridge Foundation
Reporting Period: 01 Apr 2026 to 30 Jun 2026 ¦ Nov 2025 – Jan 2030 ¦ £480,801
1. CLIENT NUMBERS
New clients this quarter | 1 | Referrals accepted in the reporting period
Total cumulative clients (project to date) | 6 | All clients registered since Feb 2025
Active cases at end of quarter | 5
Cases closed this quarter | 0
High risk cases (total) | 3 | Priority cases requiring intensive support
% of annual target met | 0% | Based on 100 clients per year target
2. BOROUGH BREAKDOWN
Clients from Ealing | 3 | 50% of all clients
Clients from Hillingdon | 2 | 33% of all clients
Clients from Hounslow | 1 | 17% of all clients
3. DEMOGRAPHICS
Clients under 25 | 0 | 0% of all clients
Female clients | 3
LGBTQ+ clients | 0
Clients with disability / health condition | 3
Clients whose first language is not English | 2
4. ACTIVITIES THIS QUARTER
Activities / events delivered | 0
Total participants reached | 0
Legal advice clinic sessions | 0
New self-referrals generated from activities | 0
5. OUTCOMES THIS QUARTER
O1 – Clients reporting better access to legal support | 1 | Count of 'Yes' at latest assessment in this quarter
O2 – Clients with increased confidence to report | 1 | Count of 'Yes' at latest assessment in this quarter
O3 – Partnership/agency engaged | 0 | Count of 'Yes' at latest assessment in this quarter
O4 – Clients reporting increased HC awareness | 2 | Count of 'Yes' at latest assessment in this quarter
O5 – Community-led solutions initiated | 0 | Count of 'Yes' at latest assessment in this quarter
6. REFERRALS
Incoming referrals this quarter | 0
Outgoing referrals made to partners | 0
7. VOLUNTEERS & TRAINING
Active volunteers | 4
Volunteer hours this quarter | 0
Training sessions delivered this quarter | 1
Participants trained this quarter | 22
NARRATIVE SUMMARY — Replace with your commentary before sending to City Bridge Foundation:
Add your quarterly narrative here. Include key achievements, any challenges encountered, highlights from case work or community engagement, and priorities for the next quarter. This section is written for a non-specialist funder audience.

## 📖 Case Studies
CASE STUDY GENERATOR ¦ Hate Crime Support Project ¦ WLEC
Enter Client Ref in cell E5 — profile auto-populates from Client Intake & Outcome Tracker. Write narrative in sections below.
AUTO-POPULATED CLIENT PROFILE — Enter Client Ref in yellow cell below
Client Reference (type here) |  |  |  | HC/1
Client Initials |  |  |  | Freda Ritchie 1
Borough |  |  |  | Active
Date Referred |  |  |  | Omer Ul-haque
Age Group |  |  |  | Other
Gender |  |  |  | 26-55
Type of Hate Crime |  |  |  | High
Risk Level |  |  |  | Prefer not to say
Caseworker |  |  |  | FR1
Referral Source |  |  |  | Ealing
Presenting Issue |  |  |  | 0
Outcome Score (of 5 — latest) |  |  |  | Not yet assessed
✏️ BACKGROUND
Describe the client's situation when they first came to the project. What hate crime or incident were they experiencing? What impact was it having on them? (Initials only — no identifying information.)
✏️ SUPPORT PROVIDED
What did WLEC do to help? Describe casework, legal advice, advocacy, referrals, safety planning, community engagement or any other support provided.
✏️ IMPACT / OUTCOMES ACHIEVED
What changed for this client? Reference the outcome score above. How does this case demonstrate progress against the 5 project outcomes? Include direct quotes if available.
✏️ PARTNERSHIP WORKING
Which agencies or partners were involved? What did multi-agency working achieve that WLEC could not have done alone? Any MoUs, new referral pathways, or community trigger actions?
✏️ KEY LESSONS / CONTRIBUTION TO SUSTAINABILITY
What does this case demonstrate about the project's approach? Any practice changes, systemic issues identified, or contribution to building community resilience?
CASE STUDY LIBRARY — Log Completed Case Studies
Client Ref | Project Year | HC Type | Borough | Outcome Score | Funder Report Used | Notes

## ⚠ Risk Register
RISK REGISTER ¦ Hate Crime Support Project ¦ WLEC
Risks identified in M&E Framework. Update status and actions as the project progresses.
Risk | Probability | Impact | Mitigation Strategy | Owner | Review Date | Current Status | Latest Action Taken
Low engagement from hate crime victims | Medium | High | Targeted outreach via social media, trusted community leaders, and religious institutions | Outreach Coordinator | Quarterly | Active
Delays in legal case resolutions | High | Medium | Regular case review meetings; develop pro-bono legal partnerships | Casework Team Lead | Monthly | Active
Lack of police cooperation in hate crime reporting | Medium | High | Establish formal MoU with police; advocacy for better reporting mechanisms | Project Manager | Bi-annual | Active
Volunteer retention issues | Medium | Medium | Provide regular training, peer mentorship, and formal recognition programmes | Volunteer Coordinator | Quarterly | Active
Insufficient community trust in reporting | Medium | High | Community-led outreach, trusted intermediaries, translated materials | Project Manager | Quarterly | Active
Funder reporting requirements change | Low | Medium | Maintain flexible M&E framework; regular funder communication | Project Director | Bi-annual | Monitor
Key staff turnover | Low | High | Succession planning; full handover documentation; cross-training | Project Director | Annual | Monitor
Digital exclusion preventing online access | Medium | Medium | Maintain in-person and telephone support options alongside digital | Casework Team | Ongoing | Active

## ⚙ Settings
PROJECT SETTINGS & CONFIGURATION
SharePoint version history tracks who made changes and when — access via File > Version History in SharePoint/OneDrive.
Project Name |  | Hate Crime Support Project
Lead Organisation |  | West London Equality Centre (WLEC)
Funder |  | City Bridge Foundation
Total Funding |  | £480,801
Project Start Date |  | 01/11/2025
Project End Date |  | 31/10/2030
Project Duration |  | 5 Years (Nov 2025 – Oct 2030)
Current Project Year |  | Year 1 (2025-26)
Annual Client Target |  | 50
5-Year Client Target |  | 250
Boroughs Covered |  | Ealing, Hillingdon, Hounslow
Contact Email |  | freda@hrsg.org.uk
Report Prepared By
Date of Last Update
QUARTERLY REPORT CONFIGURATION — Update each quarter
Quarter Start Date |  | 2026-04-01 | Change to current quarter start
Quarter End Date |  | 30/06/2026 | Change to current quarter end
Quarter Label |  | Q1 2025-26 | e.g. Q1 2025-26
Current Year Label |  | Year 1 (2025-26) | Update each project year
Year Number (1-5) |  | 1 | Used in trend charts
5-YEAR ACTIVITY TARGETS (from framework)
Year | Cases Target | Workshops | New Volunteers
Year 1 (2025-26) | 50 | 10 | 0
Year 2 (2026-27) | 50 | 15 | 15
Year 3 (2027-28) | 50 | 15 | 0
Year 4 (2028-29) | 50 | 15 | 0
Year 5 (2029-30) | 50 | 15 | 0
REFERRAL SOURCE LIST
Victim Support
Age UK
MENCAP
Spectra
ECIL
MPS (Police)
Local MP / Councillor
Self-Referral
CATCH
Community Security Trust
Galop
MARAC
Housing Association
Council Safer Communities
Citizens Advice
Legal Aid Organisation
Hillingdon Refugee Support Organisation
Other